## Sheet1
Task # | Task/Question | Team Notes/Instructions | Duration* | Owner** | Dependencies | Deadline (EST) | Task Complete? (Initial & Date)
Deliverable | Project Management
1 | Creating the project plan |  | 2 h | Cristina | None | 2022-01-21 | Complete
2 | Create the team charter |  | 2 h | Cristina | None | 2022-01-23 | Complete
3 | Present project status reports | every two weeks, the PM will present in class | 30 min | PM of the week | 4 to 29 | every two weeks starting 1/26 | In progress
Deliverable | Research and Analysis
4 | Conduct research on the industry and the company |  | 2 h | Cristina | None | 2022-01-23 | Complete
5 | Interview with sponsor | questions on Canvas | 2 h | Cristina | None | 2022-01-23 | Complete
6 | Summarize feedback from stakeholders | summarizing the answers | 1 h | Cristina | 5 | 2022-01-23 | Complete
Deliverable | Tailored Project Plan v1
7 | Create the scope statement |  | 2h | Jason | 6 | 2022-02-06 | Complete
8 | Create the requirements document |  | 1h | Jason | 6,7 | 2022-02-06 | Complete
9 | Create the Work Breakdown Structure |  | 1 h | Jason | 8 | 2022-02-06 | Complete
Deliverable | Tailored Project Plan v2
10 | Create Stakeholder Register |  | 3 h | Yonghong | None | 2022-02-20 | Not Complete
11 | Write milestone list |  | 1 h | Yonghong | 9 | 2022-02-21 | Not Complete
12 | Develop a summary of the schedule |  | 3 h | Yonghong | 9 | 2022-02-22 | Not Complete
13 | Develop a cost statement with estimates |  | 2 h | Yonghong | 9, 12 | 2022-02-23 | Not Complete
14 | Create a communication plan |  | 1.5 h | Yonghong | 10 | 2022-02-24 | Not Complete
15 | Create an ethics staement |  | 1 h | Yonghong | None | 2022-02-25 | Not Complete
Deliverable | Tailored Project Plan v3
16 | Create Risk Register |  | 2h | Yaqiong | 12,13,9 | 2022-03-20 | Not Complete
17 | Determine Contigency Reserve |  | 1h | Yaqiong | 13 | 2022-03-20 | Not Complete
18 | Develop Human Resource Plan |  | 3h | Yaqiong | 8,12 | 2022-03-20 | Not Complete
19 | Create a Performance evaluation plan |  | 4h | Yaqiong | 11,12,14,16,18 | 2022-03-20 | Not Complete
20 | Create quality management plan |  | 4h | Yaqiong | 1,7 | 2022-03-20 | Not Complete
21 | Create a change control process and change request form |  | 2h | Yaqiong | 7,9 | 2022-03-20 | Not Complete
22 | Create Project Closure plan |  | 2h | Yaqiong | 7,10,13,18,20 | 2022-03-20 | Not Complete
23 | Develop a project lessons learn template |  | 1h | Yaqiong | None | 2022-03-20 | Not Complete
24 | Create a team lessons learn template |  | 1h | Yaqiong | None | 2022-03-20 | Not Complete
25 | Establish the project baseline |  | 1h | Yaqiong | 7,12,13 | 2022-03-20 | Not Complete
Deliverable | Draft of Sponsor Presentation
26 | Create presentation |  | 5 h | Yaqiong | 7 to 25 | 2022-03-20 | Not Complete
27 | Solicit feedback from the sponsor |  | 1 h | Yaqiong | 26 | 2022-03-20 | Not Complete
Deliverable | Final Sponsor Presentation
28 | Create the slides for the presentation |  | 5 h | Ananya | 26, 27 | 2022-03-29 | Not Complete
29 | Seek project acceptance |  | 2 h | Ananya | 28 | 2022-03-29 | Not Complete
ASSIGNMENT REVIEW
Team Feedback
30 | Read over each other's parts of the assignment |  | 30 min | Rui | 26,28 | TBD | Not Complete
Incorporate Final Edits
31 | Make changes based on team's feedback |  | 1 h | Rui | 30 | TBD | Not Complete
Formatting & Submission
32 | Review formatting and grammar |  | 30 min | Rui | 31 | TBD | Not Complete
33 | Submit assingment to Canvas |  | 10 min | Rui | 32 | TBD | Not Complete
**Resource Availability:
PM | 10h
Team member 1(Yonghong ) | 10h
Team Member 2 (Cristina) | 10h
Team Memeber 3 (Yaqiong) | 10h
Team Member 4 (Jason) | 10h
Team Member 5 (Ananya) | 10h
Team Member 6 (Rui) | 10h