## Sheet1
Risk Number | Risk Statement | Risk Owner | Risk Response | Detail of Response | Integration with Project Plan | Contingency Plan | Secondary Risk | Secondary Risk Response | Risk Status
1 | Due to the lack of understanding of the market plan by the staff, the plan was not well implemented and the publicity effect was affected. | Market Department | Mitigate | Train all marketing personnel prior to executing the marketing plan | Add work to WBS/activity list/ estimate/ schedule | Provide training | May cause delays in the implementation of the plan |  | Open
2 | Due to insufficient staff, we may not be able to implement market plans on time | HR | Mitigate | Advertise in local paper, reach out to local employers to find volunteers | Add work to WBS/activity list/ estimate/ schedule | Hire stuff | May not find efficient staff | Need to prepare training material for the new staff | Open
3 | Due to the Covid-19 travel restrickt, the activity on the critical path cannot be completed after slack time, the critical path will be change. |  | Mitigate | Work online through zoom or MsTeam to increase the weekly meeting time of the project team. | Add work to WBS/activity list/ estimate/ schedule | request change | Quality of the work may decrease | Strengthen the audit of important activities on the critical path | Open
4 | Due to the low performance on Zoom meeting, the capability of project control is low, the project may not pass the quality criteria | Quality | Mitigate | Fomulate meeting agenda and track every spint work | Raise requirements for task quality | increase testing group | the schedule may delay | Increase test personnel and frequency | Open
5
6 | [9 empty] | n/a | Probability=30% Impact=5 days EMV= 1.5 days | This requires more time and effort to fix bugs | Response required | Mitigate | Raise requirements for task quality | update the quality control criteria | 1000 | Low | Medium | increase testing group | the schedule may delay | Probability - Medium Impact - Medium | Increase test personnel and frequency